DRAFT MINUTES

PUBLIC WAYS COMMITTEE

of August 10, 2010

5:30 P.M.  City Council Chambers

COMMITTEE MEMBERS PRESENT:  	Susan Hanlon, Chairperson

John Sharkey

Beth Workman

OTHER COUNCIL MEMBERS PRESENT:  	None

OFFICIALS PRESENT:  	Service Director Chris Easton

Assistant Service Director Harry Stark

City Engineer Tom Tucker

PRESS REPRESENTATIVES:  			Katie Saxon  The Post

VISITORS SPEAKING:				None

Ms. Hanlon called the Public Ways Committee meeting of August 10, 2010 to order at 5:30 P.M.

I.    APPROVAL OF MINUTES

Ms. Workman made a motion to approve the minutes as written for the July 13, 2010 meeting of the Public Ways Committee.  Mr. Sharkey seconded.  All were in favor.  MINUTES APPROVED.

II.   PUBLIC PATICIPATION 				None

III.   PARKS & RECREATION

A.   Wadsworth Community Center Status, Transition Plan Status, Steiner Closure Timeline

Mr. Stark stated that currently the project was on schedule.  The Steiner Building had been removed.  A lot of site work had been completed at the job site.  They were currently building from east to west and were starting to lay infrastructure in the last couple of weeks.  The foundation work was going to be started this week.  They should see a structure starting to be built in the next several weeks.  The first section that was being built was the academic wing of the school.  The hope was to have that section completed before winter so they could work on the interior through the winter months.  Next year they would start on the remaining sections of the project foundation and structure.

Once the areas where the Steiner Center was located and once it was cleared a lot of the area that was being used for staging now would be moved to that location just because they were going to be starting to erect the buildings.

One of the goals of the school district was to have the track completed for the fall season and that was probably 80% completed.

Mr. Sharkey asked if Mr. Stark was saying the area where Steiner was moved was going to be used for staking.  They were originally told that that had to be taken so early because that was the way utilities came in.  Mr. Stark answered that would be for both reasons.  It was not going to be left a bare site.  They would be utilizing that because it was a vacant area now for some staging.

B.  Wadsworth Multi-Modal Transportation Plan Review

Mr. Stark began there was a public meeting last night.  Mr. Kaiser was going to email Ms. Hanlon and request that it be taken to Council.  Mr. Kaiser said that Planning Commission made a recommendation to Council for consideration of the Comprehensive Plan.

Motion on Multi-Modal Ordinance:  Ms. Workman made a motion that the Wadsworth Multi-Modal Transportation Plan Review be taken to City Council for their next meeting with their recommendation.  Mr. Sharkey seconded.  All were in favor.  MOTION WAS APPROVED.

C.   Trails Advocacy Group

Mr. Stark started looking into the Trail Project for the Community as the Committee had requested.  Originally they had talked about having that meeting at the end of the month of August.  He was thinking about delaying that a few weeks into September.  He had been having conversations with the National Park Department System as well as Medina County and Summit County.  The National Park Service would like to participate with them on that.  He needed to fine-tune that more.  In doing that, they could help facilitate some meetings for them with the public.  He was probably going to delay that public meeting until he could shore some things up with the National Park Service.   Ms. Hanlon hadn’t thought about that approach not knowing anything about it.  It sounded like a good idea, a good thing to leverage.  Mr. Stark added they had done hundreds of trail projects and worked with residents and different non-profit organizations.  Having them included in that project would be a great benefit for them.

Ms. Workman asked if that was the group that would spearhead all these that would connect the different park trails together.  Mr. Stark thought there were a number of approaches that would be looked at throughout the process.  1.  They now had a master plan, per se, for the trails and bike system.  They were really looking at how they were going to divide that into segments.  What did they want to tackle first in the development of the trails?  They wanted to get the public involved.  They wanted to possibly start a ‘Friends of Trail Group’ that would assist them throughout that process.  If that ‘Friends of Trail Group’ could become a non-profit agency that was another avenue to help generate some dollars for the project.  There were many different components for that process.  It was not going to happen quickly.  He thought the first thing they needed to do was the need to have a public meeting to come up with the different approaches and different thought concepts on the trail project and perhaps those who wanted to become a part of that core friends organization to help them spear head some of that and move on from there.

IV.   STREETS AND SIDEWLAKS

A.    State Route SR-94 Expansion Status-NOACA, TRAC Application

Mr. Tucker stated the SR-94 Expansion Status was a pretty good description of everything that had gone on with their attachment.  They were moving ahead with the contracted GPD that had been let.  They had started working on that.  They had an initial kickoff meeting with ODOT last week. They reviewed both the City’s schedule and how that schedule agreed with the ODOT schedule.   That was their big first step.  Then they would start grinding through the design.

The IMS (Interstate Modification) Study was approved by the Federal Government and they finalized their preliminary plan.  He thought that was probably the biggest thing. They submitted their fourth submittal, the access management part, to ODOT and they received a verbal approval that it was okay but they would wait for an official letter from them.

They applied for Transportation Enhancement Funds for up to $600,000 for the pedestrian bikeway access on the west side of the bridge.  They were also in the process of applying for some Tiger Funds through the Federal Government although that was looking like they might not be qualified.  He had just received the email about an hour ago.  They would have to recheck on that tomorrow.  That funding source was not going to be suitable for them.

Ms. Hanlon said on the attachment was printed PE/Corridor Study; what did PE stand for?

Mr. Tucker answered Preliminary Engineering.

B.   2009 Street Program Assessment Status

Mr. Tucker continued that the 2009 Street Program Assessment had not changed.  There was one more reading at Council for Hall Drive.   Ms. Hanlon added that after that they could take it off their agenda.

C.  Street Long Range Capital Improvement Plan-schedule of meetings, deliverables, etc.    Mr. Tucker continued with the Long Range Capital Improvement Plan that Mr. Trzcinski was able to spend some time on it and they had a draft of the first five years that utilized all of the streets that they currently had surveyed with the new survey process.  They were talking with Mr. Easton today on scheduling of inspection and on projects that were going to fall to free up some time for he and Mr. Trzcinski to spend a couple solid weeks on that.  That meant the end of August or first of September, they could free up some time, they might have to hire some subs to do inspections.  They were going to have to hire some inspectors anyway.

There were a couple emails that went out and he was trying to align with those like deliverables and things like that that would be needed.  They had a ten-year street improvement plan by neighborhood.   He wanted to address that.   They had utilized, although they were trying to tend away from the NOACA one, two, three, four, five, weighting system and go to the national PF Preservation Association Methodology that was the residual service life rating, about a third of their streets, all of the fours and fives by the old system rated, and about half or a third of the threes.   They still had quite a few of the streets that they needed to survey.   That was the rating they were going to use to itemize which streets were going to be prorated and prioritized.

In the first couple of years they were pretty solid as far as the neighborhood plan.  The next three, four, five there was a little more out there.   When they got beyond that, it was going to be a guess but the rate of change, degradation, or deterioration on each street was independent of any other street because of the age of the street, the make up of the street, the depth of the base, the depth of the asphalt, the traffic on that street, the soils in that area; there were so many factors that went to how long that street was or wasn’t going to last.  Something that was a three today, in five years it might still be a three but the other one might be a five.  There was a fair question about the process they had been doing for the last few years of the pavement preservation, he thought, they had done a lot of pavement preservation.  They had done many pavement maintenance techniques but in the last year, they had done the pavement assessments more than the pavement improvements.  He wasn’t sure what the exact question was but the pavement preservation techniques were short term where for a thin overlay they might add five to eight years.  With chip and seal, they might be adding three to five years of life.  Crack sealing might be two to three years.  Whatever that methodology was so it might take a street from a four to a three, so that a street that was naturally progressing through its life, it was a three and had ten years life before they needed to start to do something.  Or it was a three because he just added five to eight years with a thin overlay.  Six, seven or eight years from now, which one of those was going to be ready for repair.  He couldn’t tell them today.   It was hard for him to get that neighborhood by neighborhood except based on the numbers he had today.  They should realize that five years from now those streets might be different.  It was all going to be shuffled and it was all going to come true but it might not be in the same order.

Ms. Hanlon wanted to share with the public and the rest of the Committee that over the weekend Mayor Laubaugh did communicate with her and wanted her to pass on to the Committee that she was very supportive of what they were doing and very supportive of the approach they were taking and was to the point where she was ready to issue some instructions to the Administration as far as what needed to be done from that point on to move towards the ballot next May.  She had listed several pieces of information that she thought should be gathered by the Engineering Staff and it was more or less the same things they had discussed but had included a ten-year street improvement program by neighborhood and she thought what they were referring to was what they had talked about quite a while ago that example from Baton Rogue where they wanted to be able to have those meetings in the different wards to tell people they were looking at a ten-year plan, and  what was (happening) in their neighborhood right now.  They wanted to explain the process to them and ask for their feedback.  There might be a street that they were concerned about but because they didn’t live in all the neighborhoods, they were not aware.   She thought Mr. Tucker’s notion would tell them for sure what the first five years would be like, but there was a certain amount of ambiguity.   Every year they went out after that, it was more and more.  That was the best they were going to be able to do and that was the wise thing to do.  They didn’t want to lock themselves into something five or six years from now that did not make sense.

They wanted to be able to give cost of increase for taxpayers.  That was similar to what they would do with a levy or any change in income tax, that they would be able to give some examples.  Now they needed to work on the suggested ballot language and they would have to get Mr. Brague involved with that one.   They were going to have to talk through the implications of their language.  They had originally had said they wanted to earmark ten percent of income tax revenues to streets.  If they thought about what they really needed was $900,000.  If they just said they wanted to earmark ten, that first year they would only get $600,000 if their income tax revenues were only $6 million so that would mean they wanted that plus what was already being spent and she thought it got too complicated.  She thought they might have to come up with another approach.  They might say on the ballot $900,000 per year to be appropriated to a specific fund or something like that.  She didn’t know if that was legal language.  Mr. Easton said they could come up with some suggestions on the language.  Ms. Hanlon interjected to make sure it did what they wanted it to do.

Mayor Laubaugh suggested that they be ready at those meetings to present to neighborhoods how the streets had been funded in the past and at what level or lack of Street Improvements that it led to what they hadn’t been able to do with the money.  Mr. Easton thought that one of the things that had occurred (that some of the members of the public would understand) was the cost of asphalt had changed significantly over time.  They had a steady stream of gas tax revenue that used to go a lot further then than it did today.  They were not seeing as much activity in that area. Those dollars were actually declining a little bit.  He thought that kind of information pertinent to:  why were they here?  Asking was appropriate for any campaign discussion.

Ms. Hanlon thought they needed to talk about the fact if they did that, then the assessments went away.

Another thing that she Ms. Hanlon proposed to add would be -- and Mr. Tucker had referred to it -- since they started in 2009 with basically using different methods of improving the streets and preserving the streets she thought, as Council, they needed to make sure that they felt confident that those methods were working.  People might have questions about that.  Because they had tried to be innovative and tried to do things a little differently and balanced a lot of different factors, she thought it was appropriate to go back at the most five years since they had tried those different combinations of things and just do an assessment of whether it looked like it was gong to hold up the way they thought. Again, they didn’t have a crystal ball.

Mr. Tucker stated the methods like chip and seal streets, they had done 33 streets and they thought three to five years but they were sitting here at three to four years right now.   What did it look like?  Ms. Hanlon asked if chip and seal was considered preservation…Mr. Tucker said it was.  He continued that anything under eight to ten years would be considered preservation.   Ms. Hanlon would throw that out to Council, too, when they discussed it at the Committee of the Whole that if anybody had any specific concerns about anything that had been done in the last several years to fill free to ask that that would be looked at.  They wanted to make sure they were moving ahead.  Mr. Easton thought the other thing, somewhat related, was they had a concrete street that had joint failure and what was the solution, for example. Ms. Hanlon agreed.  Mr. Easton said that because they had had different maintenance techniques on that over the years. At one point, it was cut it out and re-pour it; Durapatch was another.  There were different things that they had done but what were they thinking going forward just so people had an understanding that that might not be as much as a maintenance or it was a pavement replacement.

Mr. Tucker added there were other methods that they had even tried yet.  There was white topping versus black topping where they basically go in and grind out the curb, gutter and some of the street and they put in a new thin concrete overlay.   It was expensive and it might be more suitable in some areas, perhaps on a collector street rather than a residential street.  There was crack and seal where they break the whole thing up and pave on top of it again.  Anything with a fixed curb and gutter really restrained because they were stuck with that elevation.  On the rural asphalt streets that had no curb and gutter, they could add on top a lot easier that saved the base, where with curb and gutter they had to remove and put back and somehow repair the base.  With the next ten-year program, they might try some new things along the way.  New techniques or new materials were developed every year.  New studies came out with new methodologies.  The last six months he had read about four articles that thin overlay had proven to be the most effective bang for the buck on the return for the dollar.  It was efficient done.  They were hoping to get five to eight years but they were getting eight to ten years on an overlay depending on the street.  They were not going to get that on all of them.  If they got that return on 80% or 90% of them, they had done well.   There were many trade magazines out there and they were trying to keep in touch with those things.

Mr. Sharkey said they were saying they needed to spend $900,000 a year on the streets.  Mr. Tucker explained that was the total:  maintenance, pavement preservation and improvements. When they passed the stormwater tax, Mr. Sharkey stated, about 50% of that tax went to administrative costs.  Was that going to happen with the $900,000?  If it did, they were not going to have the money to repair the streets that they needed.  Mr. Tucker couldn’t answer that question.  Mr. Sharkey thought it should be answered before they went forward. Ms. Hanlon thought that needed to be part of the ballot line.  Mr. Sharkey said that it could be a very big problem.  He wasn’t saying the money didn’t need to go to administrative but if it did, they were going to pass a tax and they would still be short funds.  Mr. Easton stated that the proposal was oriented to capital.  There were some pavement preservation things that he wasn’t sure if they were capital or maintenance.  They were going to try to come up with some language to minimize the uncertainty there.  Obviously, they wanted the dollars for capital.  That was the whole discussion.  They didn’t want the funds necessarily for operations.

On the other hand, they had to be flexible and understand that every year the street improvement program was going to be oriented towards projects.  Not every project year was going to $900,000.   They might have a million one year and $800,000 the next.  There was a little bit of flexibility.  Ms. Hanlon added that they didn’t necessarily have to spend that much but it should be collected somehow and put into a particular fund.  Mr. Easton said in a ‘capital’ type fund. Ms. Hanlon said it would be a fund that could only be used for that.  It would be silly to find themselves doing things that did not need done just to spend the money.   Mr. Easton thought the preference he would have was that the ballot language would define it into capital fund.  Then the Council would control that capital.  It was capital improvements’ fund.

Ms. Hanlon said that the other item that the Mayor brought up to talk about with the Committee of the Whole that they would need that information by October 1 to be able to keep on schedule to go out to have the meetings in October where they ask their taxpayers if they were interested in this.  That was the notion if they got a big ‘no,’ now was not the time to do it, they didn’t want to hear about it, then they didn’t.  They would go back some other time and regroup.  The Mayor rightly encouraged them at those meetings that every ward person should be at their ward meeting as well as at-large Council people.  When they started to schedule those meetings, they were going to make sure around at least the ward Council persons availability or commitment that they would be there.  Mr. Easton continued that they were thinking to schedule those in late October or early November.  They might have only one per ward and then one central meeting perhaps.  That way they had given folks plenty of opportunity for feedback in their neighborhoods and in total.  Ms. Hanlon was sure that any visuals that they came up with and all the information they could create should be placed on their website.  If someone couldn’t go to the meeting, they could go to the website to see the power point presentations or whatever, and perhaps some maps, added Mr. Easton.   Ms. Hanlon said they were moving along, and indicated she was glad the Mayor had weighed-in and been so supportive of the issue.

D.   2010 Street Improvement Program

Mr. Tucker said that the Great Oaks Trail was a $260,000 grant that they received through Issue One.  They bid that last week and Barbicus out of Cuyahoga Falls was the low bid.  They met with them with the pre-bid award meeting because they hadn’t worked with them specifically so he stilled that a few years ago that they should sit down to meet with them before they close the contract to make sure that they were fully aware of what they did bid on and the City was very clear in what was expected.  That had been helpful.  The Board of Control was signed off on the contract as well.  They could move forward rather quickly.  However, their schedule wouldn’t allow them to get here until the middle of September.  Their completion date was October 15.  Ms. Hanlon questioned that street was closed right now.  Mr. Tucker said it was closed now because as part of the grant, they had to provide 10% matching funds that worked out perfectly with the amount of full depth joint repairs and slab repairs that needed to be completed.   Their street department was the ones that worked up a nice job because there were large sections where the soil was really bad.  They were readjusting the catch basins to grade and many of those had to be repaired anyway because the slabs around the catch basins were the basins themselves.  That worked well with their annual catch basin repair program.

That work was going on now with the street crews performing the work.  The contractor would be utilizing the same detour because the work at the intersection with the two left turns coming from High Street was pretty tight so they would be detouring at night so they were not interfering with businesses until late night.  Even then, there would be lanes open:  the south lane would be open when the north was detoured so they could get into the businesses that were open at that time.  They were really trying to be conscientious about the businesses, the traffic and interference.  The downside of that they would have noise at night and they might get some complaints in that regard.   He thought most of the night work would be done in the commercial area, and would be done more in the evening in the residential area.

Ms. Workman had a question because several people had been asking about those street closures.   She said that Mr. Tucker had stated that the main contractor would start in mid-September.  What the street department was doing right now, would that continue to mid-September?  They should be finished in the next two weeks, Mr. Tucker said.  That was their schedule, thinking that the contractor would start late August or early September.  The contractor was going to be two to three weeks later than they had anticipated before he got through the contracts that he already had.  Ms. Hanlon asked when the project would be completed.  Mr. Tucker said their closeout was October 15.  The contractor thought they would be done before that.

Mr. Tucker continued that in addition they had Leatherman Road was going to have a thin overlay with partial depth repairs in some places.  He thought they were going to wait until Fernwood and Prospect that were pavement improvement projects that they could not advertise until August 20, he thought.  So they would be letting that in the first week in September and by the time, they got through contracts.  The work on Leatherman would probably start again mid to late September.

E.   2009 Sidewalk Program

Mr. Tucker said High Street was coming along fairly well.  They were staying off the street that had helped with traffic but there was a little more disruption to the tree lawn.  They would have a little more repair on that when they were done.  Mr. Buie thought they would be finished in another two to three weeks.

F.   2010 Sidewalk Program

Mr. Tucker continued that Mr. Buie was still inspecting and marking the Northwoods, Partridge area for the 2010 Sidewalk Program in between what he was inspecting on High Street, the 2009 Sidewalk Program.

V.   STORM WATER UTILITY

A.   NPDES Regulations/B.   College Culvert Status

Mr. Tucker they were seeing the main stormwater project on College Street.  There had been several storms in the last three weeks and the last place they wanted to be was in that large box culvert because there were 350 acres involved.   They have had about four days of delay where they put in box culverts the storms were so big they had to reset a couple of the sections the next day.   Beyond that, they were still online to be done the end of next week.  Mr. Wolf had a meeting with them today to button that up.  His plan was when they opened up on Friday of next week everything was completed.  They would have a nice project, asphalt, stripping, etc.  In the worst case, if they had more rain coming, and they were hoping everything went better than it had.  They could still open the road on the base course it would be an asphalt base, but not the surface.  They would pave the surface using one-lane closures.  Mr. Easton said so the 20th, unlike the report that said the 17th, the 20th was really the date of opening.  He thought the report talked about lane traffic maintenance.  Mr. Tucker said if they opened up on Monday, August 23, it would all have to be under traffic maintenance.  If they wait until Friday, still before school started, they would have a much better completed job.  It was a trade off.  To be fair to him, there were several days of delay due to rain.  That was what he was asking.  They were absolutely opening on Friday is what they told them today.

VI.   OTHER

Mr. Stark stated that next month he would like to begin a discussion about modifying some of their field use policies in the community.  He would bring some more information on that.

Mr. Easton asked if that was baseball fields.   Mr. Stark answered baseball fields primarily.

Ms. Hanlon said they would add that to the agenda for next month, and they would take off the 2009 Street Assessment Program.

Their next meeting would be held September 14, at 5:30 p.m.

ADJOURNMENT:  Mr. Sharkey made a motion that they adjourn, which was seconded by Ms. Workman.  All were in favor.  The meeting was adjourned at 6:10 p.m.

____________________		__________________________

Chairperson				Date approved